## Feature List
Apartment Building Management System - Detailed Feature List
Overwritten in place on 2026-03-18. Added React parity updates for login, resident, staff, apartment, billing, bookings, and activity.
# | Feature Name | Function Name | Screen Name | Actor(Users) | Complexity | Planned Code Iteration | Student No | Student Name | SRS Status | Design Status | Coding Status | Testcase Status | Test Status | Description
1 | Apartment Administration | Assign apartment unit to resident | Flutter ApartmentScreen | Admin | Medium | Current | HE182023 | Le Minh Duc | Done | Done | Done | Partial | Partial | Persisted flow, no longer UI-only.
2 | Apartment Administration | Create apartment unit | Flutter ApartmentScreen | Admin | Medium | Current | HE182023 | Le Minh Duc | Done | Done | Done | Partial | Partial | Apartment creation persists.
3 | Apartment Administration | Deactivate apartment unit | Flutter ApartmentScreen | Admin | Low | Current | HE182023 | Le Minh Duc | Done | Done | Done | Partial | Partial | Apartment deactivation persists.
4 | Apartment Administration | Export apartment administration data | Flutter ApartmentScreen | Admin | Low | Current | HE182023 | Le Minh Duc | Done | Done | Partial | Not Started | Not Started | Uses FileSaver in Flutter, but real file download/save on device has not been verified end-to-end.
5 | Apartment Administration | Filter apartment units by status | Flutter ApartmentScreen | Admin | Low | Current | HE182023 | Le Minh Duc | Done | Done | Done | Not Started | Not Started | Statuses: All, Occupied, Vacant, Assigned, Deactivated.
6 | Apartment Administration | Reactivate apartment unit | Flutter ApartmentScreen | Admin | Low | Current | HE182023 | Le Minh Duc | Done | Done | Done | Partial | Partial | Apartment activation persists.
7 | Apartment Administration | Search apartment units | Flutter ApartmentScreen | Admin | Low | Current | HE182023 | Le Minh Duc | Done | Done | Done | Not Started | Not Started | Client-side search is available.
8 | Apartment Administration | Update apartment unit | Flutter ApartmentScreen | Admin | Medium | Current | HE182023 | Le Minh Duc | Done | Done | Done | Partial | Partial | Apartment update persists.
9 | Apartment Administration | View apartment unit details | Flutter ApartmentScreen | Admin | Low | Current | HE182023 | Le Minh Duc | Done | Done | Done | Not Started | Not Started | Details dialog is available.
10 | Apartment Administration | View apartment unit stats and list | Flutter ApartmentScreen | Admin | Medium | Current | HE182023 | Le Minh Duc | Done | Done | Done | Partial | Partial | Loads from billing-service /apartments.
11 | Authentication & Account | Change password | Flutter ResidentAccountScreen | Resident / Staff / Admin | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Uses /users/{id}/change-password.
12 | Authentication & Account | Complete password reset | Flutter ResetPasswordFlowScreen | Admin / Resident / Staff | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Uses /auth/reset-password/complete.
13 | Authentication & Account | Fetch account profile | Flutter ResidentAccountScreen | Resident / Staff / Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Uses /users/{id}/account.
14 | Authentication & Account | Fetch account settings payload | Auth API | Resident / Staff / Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Uses /users/{id}/settings.
15 | Authentication & Account | Fetch user by email after Google sign-in | Flutter AuthProvider | Admin / Resident / Staff | Low | Current | Team | Team | Done | Done | Partial | Not Started | Not Started | Falls back to client session when backend user is missing.
16 | Authentication & Account | Fetch user profile by id | Auth API | Admin / Resident / Staff | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Uses /users/{id}.
17 | Authentication & Account | Google Sign-In on Flutter | Flutter LoginScreen | Admin / Resident / Staff | Medium | Current | Team | Team | Done | Done | Partial | Not Started | Not Started | Google sign-in exists but role mapping still has fallback logic.
18 | Authentication & Account | Handle login error messages by category | Flutter AuthProvider | Admin / Resident / Staff | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Flutter maps auth failures to controlled messages.
19 | Authentication & Account | Login with email, password, and role selection | Flutter LoginScreen | Admin / Resident / Staff | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Auth-service login is used by Flutter.
20 | Authentication & Account | Logout and clear local session | Flutter account | Admin / Resident / Staff | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Client-side logout is available in Flutter.
21 | Authentication & Account | Password strength indicator (Weak/Fair/Good/Strong) updates while typing | Flutter ResetPasswordFlowScreen | Admin / Resident / Staff | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Strength is calculated from length and character classes and updates onChange.
22 | Authentication & Account | Request password reset OTP | Flutter ResetPasswordFlowScreen | Admin / Resident / Staff | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Uses /auth/reset-password/request-otp.
23 | Authentication & Account | Verify password reset OTP | Flutter ResetPasswordFlowScreen | Admin / Resident / Staff | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Uses /auth/reset-password/verify-otp.
24 | Billing & Payment | Create invoice | Flutter BillingScreen | Admin | High | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Invoice creation persists and can queue email.
25 | Billing & Payment | Create PayOS checkout session | Flutter ResidentBillsScreen | Resident | High | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Uses billing checkout endpoint.
26 | Billing & Payment | Deactivate invoice | Flutter BillingScreen | Admin | Low | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Invoice deactivation persists.
27 | Billing & Payment | Display PayOS cancel page | billing-service browser route | Resident | Low | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Cancel page exists in billing-service.
28 | Billing & Payment | Display PayOS return page | billing-service browser route | Resident | Low | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Return page exists in billing-service.
29 | Billing & Payment | Export invoices | Flutter BillingScreen | Admin | Low | Current | HE180259 | Pham Duc Thanh | Done | Done | Partial | Not Started | Not Started | Uses FileSaver in Flutter, but real file download/save on device has not been verified end-to-end.
30 | Billing & Payment | Filter invoices by status | Flutter BillingScreen | Admin | Low | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Not Started | Not Started | Statuses: All, Paid, Pending, Overdue, Deactivated.
31 | Billing & Payment | In-app notification when invoice is paid (webhook-driven) | Flutter Notifications | Resident | Medium | Next | Team | Team | Planned | Planned | Not Started | Not Started | Not Started | Resident should receive a notification after PayOS webhook marks invoice as Paid.
32 | Billing & Payment | Mark invoice as paid | Flutter ResidentBillsScreen | Admin / Resident | Medium | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Uses billing pay endpoint.
33 | Billing & Payment | Reactivate invoice | Flutter BillingScreen | Admin | Low | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Invoice status update persists.
34 | Billing & Payment | Receive PayOS webhook | billing-service webhook | System | High | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Webhook endpoint updates payment state.
35 | Billing & Payment | Search invoices | Flutter BillingScreen | Admin | Low | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Not Started | Not Started | Client-side search is available.
36 | Billing & Payment | Send invoice email | Flutter BillingScreen | Admin | Medium | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Requires valid SMTP env vars.
37 | Billing & Payment | Update invoice | Flutter BillingScreen | Admin | Medium | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Invoice update persists.
38 | Billing & Payment | View billing overview | Flutter BillingScreen | Admin | Medium | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Partial | Partial | Billing overview loads from billing-service.
39 | Billing & Payment | View invoice details | Flutter BillingScreen | Admin | Low | Current | HE180259 | Pham Duc Thanh | Done | Done | Done | Not Started | Not Started | Details dialog is available.
40 | Dashboards & Navigation | Export resident billing statement | Flutter ResidentBillsScreen | Resident | Low | Current | Team | Team | Done | Done | Partial | Not Started | Not Started | Uses FileSaver in Flutter, but real file download/save on device has not been verified end-to-end.
41 | Dashboards & Navigation | Export staff settings configuration | Flutter StaffSettingsScreen | Staff | Low | Current | Team | Team | Done | Done | Partial | Not Started | Not Started | Uses FileSaver in Flutter, but real file download/save on device has not been verified end-to-end.
42 | Dashboards & Navigation | Logout from resident account | Flutter ResidentAccountScreen | Resident | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Logout is available.
43 | Dashboards & Navigation | Quick action book gym | Flutter ResidentDashboardScreen | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Starts real booking flow.
44 | Dashboards & Navigation | Quick action book pool | Flutter ResidentDashboardScreen | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Starts real booking flow.
45 | Dashboards & Navigation | Quick action navigate to resident bills | Flutter ResidentDashboardScreen | Resident | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Opens resident bills screen.
46 | Dashboards & Navigation | Quick action open help desk or security | Flutter ResidentDashboardScreen | Resident | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Opens resident security screen.
47 | Dashboards & Navigation | Refresh admin dashboard | Flutter AdminDashboardScreen | Admin | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Manual refresh is available.
48 | Dashboards & Navigation | Save staff settings configuration | Flutter StaffSettingsScreen | Staff | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Helper utility only.
49 | Dashboards & Navigation | Update staff pricing tier values | Flutter StaffSettingsScreen | Staff | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Helper utility only.
50 | Dashboards & Navigation | View admin dashboard overview | Flutter AdminDashboardScreen | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Dashboard shows live summary and navigation.
51 | Dashboards & Navigation | View resident account profile | Flutter ResidentAccountScreen | Resident | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Loads account data from auth-service.
52 | Dashboards & Navigation | View resident bills list | Flutter ResidentBillsScreen | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Loads resident bills from billing-service.
53 | Dashboards & Navigation | View resident dashboard overview | Flutter ResidentDashboardScreen | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Loads bookings, announcements, and bills.
54 | Dashboards & Navigation | View staff dashboard overview | Flutter StaffDashboardScreen | Staff | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Dashboard provides shortcuts and summary cards.
55 | Dashboards & Navigation | View staff facilities work queue screen | Flutter StaffFacilitiesScreen | Staff | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Uses real assigned-task data.
56 | Dashboards & Navigation | View staff security screen | Flutter StaffSecurityScreen | Staff | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Uses real history and SOS flow.
57 | Facility & Service Management | Add maintenance log entry | Flutter FacilitiesScreen | Admin / Staff | Medium | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Uses facility log endpoint.
58 | Facility & Service Management | Assign facility work to staff | Flutter FacilitiesScreen | Admin | High | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Creates operations task for selected staff.
59 | Facility & Service Management | Create facility or service | Flutter FacilitiesScreen | Admin | Medium | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Facility creation persists.
60 | Facility & Service Management | Deactivate facility or service | Flutter FacilitiesScreen | Admin | Low | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Facility deactivation persists.
61 | Facility & Service Management | Export facility and service data | Flutter FacilitiesScreen | Admin | Low | Current | HE181478 | Cao Doanh Chinh | Done | Done | Partial | Not Started | Not Started | Uses FileSaver in Flutter, but real file download/save on device has not been verified end-to-end.
62 | Facility & Service Management | Reactivate facility or service | Flutter FacilitiesScreen | Admin | Low | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Facility activation persists.
63 | Facility & Service Management | Search facility and service list | Flutter FacilitiesScreen | Admin | Low | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Not Started | Not Started | Client-side search is available.
64 | Facility & Service Management | Update facility or service | Flutter FacilitiesScreen | Admin | Medium | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Facility update persists.
65 | Facility & Service Management | View facility and service list | Flutter FacilitiesScreen | Admin | Medium | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Facility list loads from facility-service.
66 | Facility & Service Management | View facility or service details | Flutter FacilitiesScreen | Admin | Low | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Not Started | Not Started | Details dialog is available.
67 | Operations & Assignment | Create staff task | FacilitiesScreen, SecurityScreen assignment flows | Admin | High | Current | Team | Team | Done | Done | Done | Partial | Partial | Operations task creation persists.
68 | Operations & Assignment | Open assigned facility job details | Flutter StaffFacilitiesScreen | Staff | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Assignment detail dialog is available.
69 | Operations & Assignment | View admin activity feed | Flutter AdminActivityScreen | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Loads activity from operations-service.
70 | Operations & Assignment | View staff assigned task queue | Flutter StaffFacilitiesScreen | Staff | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Loads assigned tasks from operations-service.
71 | Operations Dispatch | Assign custom service request to staff (admin) | Flutter FacilitiesScreen (Custom Service Requests section) | Admin | Medium | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Admin assigns request to a staff member; staff only sees assigned requests.
72 | Operations Dispatch | Quote custom service request (staff proposes price before accepting job) | Flutter StaffFacilitiesScreen | Staff | Medium | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Staff submits quote; resident must confirm before job is accepted.
73 | Resident Management | Create resident | Flutter ResidentListScreen | Admin | Medium | Current | HE180151 | Do Xuan Phong | Done | Done | Done | Partial | Partial | Resident creation persists through auth-service.
74 | Resident Management | Deactivate resident | Flutter ResidentListScreen | Admin | Low | Current | HE180151 | Do Xuan Phong | Done | Done | Done | Partial | Partial | Resident deactivation persists.
75 | Resident Management | Export resident management CSV | Flutter ResidentListScreen | Admin | Low | Current | HE180151 | Do Xuan Phong | Done | Done | Partial | Not Started | Not Started | Uses FileSaver in Flutter, but real file download/save on device has not been verified end-to-end.
76 | Resident Management | Filter resident list by status | Flutter ResidentListScreen | Admin | Low | Current | HE180151 | Do Xuan Phong | Done | Done | Done | Not Started | Not Started | Statuses: All, Active, Deactivated.
77 | Resident Management | Reactivate resident | Flutter ResidentListScreen | Admin | Low | Current | HE180151 | Do Xuan Phong | Done | Done | Done | Partial | Partial | Resident activation persists.
78 | Resident Management | Search resident list | Flutter ResidentListScreen | Admin | Low | Current | HE180151 | Do Xuan Phong | Done | Done | Done | Not Started | Not Started | Client-side search is available.
79 | Resident Management | View resident details | Flutter ResidentListScreen | Admin | Low | Current | HE180151 | Do Xuan Phong | Done | Done | Done | Not Started | Not Started | Details dialog is available.
80 | Resident Management | View resident list | Flutter ResidentListScreen | Admin | Low | Current | HE180151 | Do Xuan Phong | Done | Done | Done | Partial | Partial | Resident list loads from auth-service.
81 | Resident Services & Booking | Book paid AC cleaning service | Flutter ResidentBookingsScreen (Services tab) | Resident | Medium | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Paid in-unit service booking persists.
82 | Resident Services & Booking | Book paid home repair service | Flutter ResidentBookingsScreen (Services tab) | Resident | Medium | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Paid in-unit service booking persists.
83 | Resident Services & Booking | Book paid housekeeping service | Flutter ResidentBookingsScreen (Services tab) | Resident | Medium | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Paid in-unit service booking persists.
84 | Resident Services & Booking | Book shared facility slot | Flutter ResidentBookingsScreen (Services tab) | Resident | Medium | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Creates real booking records.
85 | Resident Services & Booking | Browse resident service cards | Flutter ResidentBookingsScreen (Services tab) | Resident | Low | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Shows shared and paid services from backend data.
86 | Resident Services & Booking | Create monthly parking subscription | Flutter ResidentBookingsScreen (Services tab) | Resident | High | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Monthly price is 800000.
87 | Resident Services & Booking | Create yearly parking subscription | Flutter ResidentBookingsScreen (Services tab) | Resident | High | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Yearly price is 8400000.
88 | Resident Services & Booking | Select car parking slot from 5 x 6 layout | Flutter ResidentBookingsScreen (Services tab) | Resident | Medium | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Car-only slot selection supports A1..E6.
89 | Resident Services & Booking | View resident announcements | Flutter ResidentBookingsScreen (Services tab) | Resident | Low | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Loads announcements from facility-service.
90 | Resident Services & Booking | View resident bookings list | Flutter ResidentBookingsScreen (Services tab) | Resident | Low | Current | HE181478 | Cao Doanh Chinh | Done | Done | Done | Partial | Partial | Loads booking history from facility-service.
91 | Resident Services (Paid) | Confirm or reject quote for custom service request (resident) | Flutter ResidentBookingsScreen (Services tab) | Resident | Medium | Current | Team | Team | Done | Done | Done | Not Started | Not Started | On reject, request moves to reassign state for admin.
92 | Resident Services (Paid) | Create custom service request (resident enters description, zone, schedule) | Flutter ResidentBookingsScreen (Services tab) | Resident | Medium | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Creates an operations custom service request that admin can assign to staff.
93 | Security & Reporting | Assign incident to staff | Flutter SecurityScreen | Admin | High | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Creates operations task for selected staff.
94 | Security & Reporting | Create security incident | Flutter SecurityScreen, ResidentSecurityScreen | Admin / Resident | Medium | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Incident creation persists.
95 | Security & Reporting | Deactivate security incident | Flutter SecurityScreen | Admin | Low | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Incident deactivation persists.
96 | Security & Reporting | Export security incident data | Flutter SecurityScreen | Admin | Low | Current | HE182112 | Nguyen Thanh Long | Done | Done | Partial | Not Started | Not Started | Uses FileSaver in Flutter, but real file download/save on device has not been verified end-to-end.
97 | Security & Reporting | Reactivate security incident | Flutter SecurityScreen | Admin | Low | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Status update persists.
98 | Security & Reporting | Resident incident report form | Flutter ResidentSecurityScreen | Resident | Medium | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Submits non-SOS incident report.
99 | Security & Reporting | Resident security history | Flutter ResidentSecurityScreen | Resident | Low | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Loads resident history from security-service.
100 | Security & Reporting | Resident SOS alert | Flutter ResidentSecurityScreen | Resident | Medium | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Triggers real SOS incident.
101 | Security & Reporting | Staff security history | Flutter StaffSecurityScreen | Staff | Low | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Loads staff history from security-service.
102 | Security & Reporting | Staff SOS alert | Flutter StaffSecurityScreen | Staff | Medium | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Triggers real SOS incident.
103 | Security & Reporting | Update security incident | Flutter SecurityScreen | Admin | Medium | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Incident update persists.
104 | Security & Reporting | View security incident details | Flutter SecurityScreen | Admin | Low | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Not Started | Not Started | Details dialog is available.
105 | Security & Reporting | View security overview | Flutter SecurityScreen | Admin | Medium | Current | HE182112 | Nguyen Thanh Long | Done | Done | Done | Partial | Partial | Loads overview and incidents from security-service.
106 | Staff Management | Create staff member | Flutter StaffListScreen | Admin | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Staff creation persists.
107 | Staff Management | Deactivate staff member | Flutter StaffListScreen | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Staff deactivation persists.
108 | Staff Management | Export staff directory | Flutter StaffListScreen | Admin | Low | Current | Team | Team | Done | Done | Partial | Not Started | Not Started | Uses FileSaver in Flutter, but real file download/save on device has not been verified end-to-end.
109 | Staff Management | Filter staff by shift or status | Flutter StaffListScreen | Admin | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Filter chips and sorting are available.
110 | Staff Management | Reactivate staff member | Flutter StaffListScreen | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Staff activation persists.
111 | Staff Management | Search staff list | Flutter StaffListScreen | Admin | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Client-side search is available.
112 | Staff Management | Update staff member | Flutter StaffListScreen | Admin | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Staff update persists.
113 | Staff Management | View staff details | Flutter StaffListScreen | Admin | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Details dialog is available.
114 | Staff Management | View staff list | Flutter StaffListScreen | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Staff list loads from auth-service.
115 | Operations Activity | View admin activity feed | React AdminActivity | Admin | Medium | Current | Team | Team | Done | Done | Done | Not Started | Not Started | React admin activity page now loads operations-service activity feed.
116 | Resident Services | View resident services and bookings | React ResidentBookings | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Resident bookings page loads facilities, bookings, announcements, and custom requests.
117 | Resident Services | Create resident facility booking | React ResidentBookings | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | React resident can create bookings and trigger invoice creation for paid services.
118 | Resident Services | Create custom service request | React ResidentBookings | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Custom service requests persist through operations-service.
119 | Resident Services | Respond to custom service quote | React ResidentBookings | Resident | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Resident can confirm or reject quoted custom service requests.
120 | Resident Billing | View resident bills | React ResidentBills | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Resident bills page loads real billing-service data.
121 | Resident Billing | Open PayOS checkout for resident bill | React ResidentBills | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | React resident can open checkout URL generated by billing-service.
122 | Resident Billing | Export resident statement | React ResidentBills | Resident | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | CSV statement download is available in the React resident billing page.
123 | Resident Account | View account summary | React ResidentAccount | Resident | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | Account summary now loads from auth-service account endpoint.
124 | Resident Account | Change password from account page | React ResidentAccount | Resident | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | React resident account page now submits password changes to auth-service.
125 | Resident Management | Create resident | React ResidentList | Admin | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | React resident management now creates resident records through auth-service.
126 | Resident Management | Deactivate resident | React ResidentList | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | React resident management can deactivate resident records.
127 | Resident Management | Reactivate resident | React ResidentList | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | React resident management can reactivate resident records.
128 | Resident Management | View resident details | React ResidentList | Admin | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Resident details modal is available in the React admin page.
129 | Staff Management | Create staff member | React StaffList | Admin | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | React staff directory now creates staff records through auth-service.
130 | Staff Management | Update staff member | React StaffList | Admin | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | React staff directory can update staff records.
131 | Staff Management | Deactivate staff member | React StaffList | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | React staff directory can deactivate staff records.
132 | Staff Management | Reactivate staff member | React StaffList | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | React staff directory can reactivate staff records.
133 | Staff Management | View staff details | React StaffList | Admin | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Staff details modal is available in the React admin page.
134 | Apartment Administration | Create apartment unit | React Apartment | Admin | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | React apartment page can create units via billing-service.
135 | Apartment Administration | Update apartment unit | React Apartment | Admin | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | React apartment page can update unit information.
136 | Apartment Administration | Assign apartment unit to resident | React Apartment | Admin | Medium | Current | Team | Team | Done | Done | Done | Partial | Partial | Assign action now updates resident name and status in React apartment administration.
137 | Apartment Administration | Deactivate apartment unit | React Apartment | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | React apartment page can deactivate units.
138 | Apartment Administration | Reactivate apartment unit | React Apartment | Admin | Low | Current | Team | Team | Done | Done | Done | Partial | Partial | React apartment page can reactivate deactivated units.
139 | Apartment Administration | View apartment unit details | React Apartment | Admin | Low | Current | Team | Team | Done | Done | Done | Not Started | Not Started | Unit details modal is available in the React apartment page.
140 | Authentication | Render Flutter-aligned login portal | React Login | Resident, Staff, Admin | Medium | Current | Team | Team | Done | Done | Done | Not Started | Not Started | React login layout was reworked to follow the Flutter login screen structure more closely.